## Sheet1
ID | SP | User story | Task | AC | Estimation | Assignee
1 | 1 | As a user, I want to bind my account with a care facility, so I can call the specific care facility workers to take care of me. | Design a main page about care facility information | This page contains the name, address, picture, contact information and brief introduction of the maintenance organization. | 2h | Oskar
|  |  | Let the doctors information page could interact with care facility information | The care facility page could successfully interact with doctors information page. | 2h | Benjamin
2 | 1 | As a doctor, I want to use the Hospital uploads/user uploads user's health test report via software function, so that I can easily let patient get their health report. | Design a health report viewing interface | Doctors can view uploaded patient health reports through this interface | 4h | Jarvis
3 | 4 | As a patient's family member, when my family members are sudd enly ill, I hope the hospital can provide services so that we can reach the hospital quickly. | Design a new hospital selection interface | Users can choose different hospitals according to their needs. | 4h | Orlando
|  |  | Design an interface for hospitals to provide help | Users can choose the services they need according to their needs.（Services include (call an ambulance, online ambulance guidance, drug demand, medical consultation, etc.)） | 4h | Jim
|  |  | Design the interface for hospitals to provide services | Users can choose the service they want according to their needs. | 1h | Ethan
|  |  | Design the interface to choose the hospital | Users can accurately choose the hospital they want through the interface.. | 1h | Alex